## TEST PLAN
TEST PLAN
Field | Details
Project Name: | Notes Application – UI & API Hybrid Testing
Test Plan ID: | TP-001
Version: | 1
Date: | 2026-05-06
Prepared By: | Sanjana Maroju
Approved By: | [Trainer/Faculty Name]
SCOPE
Field | Details
Features to be Tested: | 1. UI Login Functionality
2. Note Creation through UI
3. API GET /notes Validation
4. UI → API Data Synchronization
5. Delete Note via API
6. API → UI Synchronization
7. Negative UI & API Validations
8. API Authentication Validation
9. UI Instant DOM Update Validation
TESTING TYPE
Testing Type | Applicable
Functional Testing | ☑
Regression Testing | ☑
Integration Testing | ☑
UAT | ☐
TEST ENVIRONMENT
Field | Details
Environment: | QA / Staging
Browser/OS: | Chrome / Windows 11
API Tool: | Swagger UI / Postman
Network: | Stable Internet Connection
TIMELINE
Field | Details
Start Date: | 2026-05-06
End Date: | 2026-05-08
RESOURCES
Field | Details
QA Lead: | Sanjana Maroju
QA Resources: | QA Tester
Test Data Provider: | Manual Test Data / API Responses
Tools Used: | Chrome Browser, Swagger UI, Postman, Excel
RISKS & ASSUMPTIONS
Field | Details
Risks: | API downtime, unstable internet connection, token expiration issues, UI locator changes
Assumptions: | Application and APIs are accessible, valid credentials available, stable environment configured, Swagger authentication functioning properly

## TEST SCENARIOS
Scenario ID | Module | Scenario Description | Priority
TS-01 | Login | Validate successful UI login | High
TS-02 | Notes | Validate note creation through UI | High
TS-03 | Notes | Validate note appears instantly without refresh | Medium
TS-04 | API | Validate GET /notes API returns notes | High
TS-05 | Hybrid | Validate UI-created note matches API response | High
TS-06 | API | Validate note deletion through API | High
TS-07 | Hybrid | Validate API-deleted note disappears from UI | High
TS-08 | UI Negative | Validate empty or invalid UI inputs | Medium
TS-09 | API Negative | Validate invalid API requests | Medium

## TEST CASES
Test Case ID | Scenario ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Priority | Severity
TC-UI-01 | TS-01 | Validate successful login | User registered | Open app → Enter credentials → Click Login | Valid username/password | User should login successfully | High | Critical
TC-UI-02 | TS-02 | Validate note creation | User logged in | Click Add Note → Enter details → Save | Title & Description | Note should be created | High | Major
TC-UI-03 | TS-03 | Validate instant UI update | Note created | Observe notes list after save | Sample note | Note appears instantly | Medium | Major
TC-API-01 | TS-04 | Validate GET /notes API | API accessible | Send GET request | Endpoint URL | Status 200 with notes list | High | Critical
TC-E2E-01 | TS-05 | Validate UI → API consistency | Note created in UI | Capture UI data → Call API → Compare | Note details | UI and API data match | High | Critical
TC-API-02 | TS-06 | Validate DELETE note API | Note exists | Send DELETE request | Note ID | Note deleted successfully | High | Critical
TC-E2E-02 | TS-07 | Validate API → UI synchronization | Note deleted via API | Refresh UI → Check notes | Deleted note | Deleted note not visible | High | Major
TC-NEG-01 | TS-08 | Validate empty fields | User logged in | Leave fields empty → Save | Empty input | Validation message displayed | Medium | Minor
TC-NEG-02 | TS-09 | Validate invalid API request | API available | Send invalid request | Invalid endpoint | Proper error returned | Medium | Major

## TEST DATA
Test Data ID | Test Data Type | Test Data Values | Purpose
TD-001 | Valid User | Username: sanjana@gmail.com, Password: testuser@123 | Valid login scenarios
TD-002 | Invalid User | Username: invalid@example.com, Password: Wrong@123 | Negative login validation
TD-003 | Valid Note Data | Title: Test Note, Description: Sample Description | Note creation validation
TD-004 | Invalid Note Data | Title: "", Description: "" | Empty field validation
TD-005 | Long Input Data | Title: 256+ characters string | Boundary/edge case testing
TD-006 | Special Character Data | Title: @#$%^&*, Description: !@#Test | Special character validation
TD-007 | API Endpoint Data | GET /notes, DELETE /notes/{id} | API testing scenarios
TD-008 | Invalid API Request | Invalid endpoint /wrongnotes | Negative API validation
TD-009 | Response Time Data | Expected response time < 2 sec | Performance validation
TD-010 | Deleted Note Data | Deleted note title and ID | API → UI synchronization validation

## TEST EXECUTION REPORT
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-UI-01 | Cycle-1 | Login with valid credentials | QA-User1 | 2026-05-06 | Pass |  | Executed successfully
TC-UI-02 | Cycle-1 | Create note through UI | QA-User1 | 2026-05-06 | Pass |  | Note created successfully
TC-UI-03 | Cycle-1 | Validate instant UI update | QA-User1 | 2026-05-06 | Pass |  | Note displayed without refresh
TC-API-01 | Cycle-1 | Validate GET /notes API | QA-User2 | 2026-05-06 | Pass |  | API returned status 200
TC-E2E-01 | Cycle-1 | Validate UI → API consistency | QA-User2 | 2026-05-06 | Pass |  | UI and API data matched
TC-API-02 | Cycle-1 | Validate DELETE note API | QA-User2 | 2026-05-06 | Pass |  | Note deleted successfully
TC-E2E-02 | Cycle-1 | Validate API → UI synchronization | QA-User1 | 2026-05-06 | Pass |  | Deleted note removed from UI
TC-NEG-01 | Cycle-1 | Validate empty note fields | QA-User1 | 2026-05-06 | Pass |  | Validation message displayed
TC-NEG-02 | Cycle-1 | Validate invalid API request | QA-User2 | 2026-05-06 | Pass |  | Proper error response returned

## TRACEABILITY MATRIX (RTM)
Req ID | Requirement Description | Scenario ID | Test Case ID | Coverage Status
FR-01 | UI login should work | TS-01 | TC-UI-01 | Covered
FR-02 | Create note via UI | TS-02 | TC-UI-02 | Covered
FR-03 | Note appears instantly in UI | TS-03 | TC-UI-03 | Covered
FR-04 | API GET /notes returns list | TS-04 | TC-API-01 | Covered
FR-05 | UI-created note appears in API | TS-05 | TC-E2E-01 | Covered
FR-06 | Delete note via API | TS-06 | TC-API-02 | Covered
FR-07 | Deleted note disappears from UI | TS-07 | TC-E2E-02 | Covered
FR-08 | API response < 2 sec | TS-04 | TC-API-01 | Covered
FR-09 | Negative scenarios | TS-08, TS-09 | TC-NEG-01, TC-NEG-02 | Covered

## DEFECT REPORT
Defect ID | Defect ID | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
| N/A | N/A | No defects identified during test execution | N/A | Application should function as expected | Application functioned as expected | N/A | N/A | Closed

## TEST SUMMARY REPORT
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | Notes Application – UI & API Hybrid Testing
Test Cycle: | Cycle-1
Report Date: | 2026-05-06
Prepared By: | Sanjana Maroju
EXECUTION SUMMARY
Total Test Cases: | 9
Test Cases Executed: | 9
Test Cases Passed: | 9
Test Cases Failed: | 0
Pass Percentage: | 100%
DEFECT SUMMARY
Total Defects: | 0
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 0
Low Defects: | 0
Open Defects: | 0
Closed Defects: | 0
CONCLUSION
Testing Status: | Completed
Release Readiness: | Ready for Production
Overall Recommendation: | Application successfully passed UI, API, Hybrid, and Negative validation testing
REMARKS
All planned manual test cases executed successfully. No defects identified during test execution. UI, API, and synchronization validations are functioning as expected.